## PEP
CHF |  |  | 1.1
TRM |  |  | 3800
MULTIANNUAL EXECUTION PLAN COMPASS Program, Phase II
| COMPONENTS |  |  | Quantity | Proyect Total Amount | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
[6 empty] | E | F | M | A | M | J | JL | A | S | O | N | D | E | F | M | A | M | J | JL | A | S | O | N | D | E | F | M | A | M | J | JL | A | S | O | N | D | E | F | M
| C1. Institutionalization of the Sectoral Action within ANDESCO |  |  |  | 1660999.9
|  | A1. Organizational adjustments and funding strategy for the Sectoral Action |  |  | 70000
|  |  | Capacity building and organisational adjustments plan for the integration of the Sectoral Action within ANDESCO’s core business implemented | 1 | 60000 | 2025 F: D; 2025 M: P; 2025 J: E; 2026 E: C
|  |  | Funding strategy for the Sectoral Action developed and implemented | 1 | 10000 | 2025 M: D; 2025 A: P; 2025 JL: E; 2026 E: C
|  | A2.Capacity building to strengthen the Sectoral Action towards a wider range of corporate development topics |  |  | 601500
|  |  | Monitoring and evaluation systems for new corporate development topics designed and implemented within the Sectoral Action | 1 | 27000 | 2025 M: D; 2025 A: P; 2025 JL: E; 2025 D: C
|  |  | Sectoral Action improvement plans related to new strategic corporate development indicators developed | 3 | 574500 | 2025 S: D; 2025 O: P; 2025 D: E; 2027 N: C
|  |  | Improvement Plan 1 |  |  | 2025 D: D; 2026 E: P; 2026 D: C
|  |  | Improvement Plan 2 |  |  | 2026 M: D; 2026 J: P; 2027 J: C
|  |  | Improvement Plan 3 |  |  | 2026 D: D; 2027 E: P; 2027 N: C
|  | A3. Development of public goods and knowledge management |  |  | 817999.9
|  |  | Knowledge products developed | 3 | 459999.9 | 2025 F: D; 2025 M: P; 2025 J: E; 2026 D: C
|  |  | Technical Courses developed and delivered | 2 | 140000 | 2025 F: D; 2025 M: P; 2025 J: E; 2026 D: C
|  |  | Corporate Courses developed and delivered | 2 | 140000 | 2025 F: D; 2025 M: P; 2025 J: E; 2026 D: C
|  |  | Web module for networking and knowledge exchange developed | 1 | 78000 | 2026 E: D; 2026 F: P; 2026 M: E; 2026 O: C
|  | A4. Dissemination to stakeholders at the national, regional and international level |  |  | 171500
|  |  | Dissemination plan of products and knowledge to stakeholders designed and implemented | 1 | 146500 | 2025 M: D; 2025 J: P; 2025 S: E; 2027 A: C
|  |  | International presentations delivered to position the Sectoral Action | 1 | 25000 | 2026 D: D; 2027 E: P; 2027 M: E; 2027 M: C
| C2. Institutionalization of the WOP-Colombia platform within ACODAL |  |  |  | 448000
|  | A1. Organizational adjustments and funding strategy for the WOP platform |  |  | 40000
|  |  | Capacity building and organizational adjustments plan for the integration of the WOP-Colombia within ACODAL´s core business implemented | 1 | 30000 | 2025 A: D; 2025 M: P; 2025 A: E; 2026 M: C
|  |  | Funding strategy for WOP-Colombia designed and implemented | 1 | 10000 | 2025 M: D; 2025 J: P; 2025 S: E; 2026 M: C
|  | A2.Expanding technical support between utilities based on the partnership model (peer-to-peer). |  |  | 285000
|  |  | Partnerships between water operators completed 2025 | 2 | 38000 | 2025 M: P; 2025 J: E; 2025 D: C
|  |  | Partnerships between water operators completed 2026 | 5 | 95000 | 2025 JL: P; 2025 S: E; 2026 D: C
|  |  | Partnerships between water operators completed 2027 | 8 | 152000 | bar: 2026 F to 2027 D
|  | A3. Public goods development and knowledge management |  |  | 53000
|  |  | Business cases documented | 6 | 18000 | 2025 J: D; 2025 JL: P; 2025 O: E; 2027 S: C
|  |  | Web module for networking and knowledge exchange developed | 1 | 35000 | 2025 F: D; 2025 M: P; 2025 J: E; 2025 D: C
|  | A4. Dissemination to stakeholders at the national, regional and international level |  |  | 70000
|  |  | Workshops organised to disseminate WOP-Colombia products and knowledge | 3 | 45000 | bar: 2025 J to 2025 N; 2026 A to 2026 S; 2027 A to 2027 S
|  |  | International presentations delivered to position the achievements of WOP-Colombia | 1 | 25000 | 2026 D: D; 2027 E: P; 2027 M: E; 2027 M: C
| C3. Executing Team |  |  |  | 875000
|  |  | Project Planning and Management Specialist | 1 | 311500 | 2025 E: P; 2025 F: E; 2028 E: C
|  |  | Corporate Development Specialist | 1 | 235500 | 2025 E: P; 2025 F: E; 2028 E: C
|  |  | Procurement and Administrative Specialist | 1 | 179000 | 2025 E: P; 2025 F: E; 2028 E: C
|  |  | Sector Specialist | 0.3 | 145000 | 2025 E: P; 2025 F: E; 2026 A: C
|  |  | Travel expenses (Team Leader) | 1 | 4000
| C4. Audits |  |  |  | 13600
|  |  | ACODAL audit | 1 | 13600 | 2027 A: D; 2027 S: P; 2027 D: E; 2028 F: C
| C5. Contingencies |  |  |  | 110400
|  |  | Contingencies |  | 110400
Cierre Administrativo del Programa | bar: 2028 E to 2028 M
| TOTAL |  |  |  | 3107999.9

## POA 2025
CHF |  |  | 1.1
TRM |  |  | 3800
ANNUAL OPERATING PLAN COMPASS Program, Phase II
| COMPONENTS |  |  | 2025
|  |  |  | E |  | F |  | M |  | A |  | M | J |  | JL | A | S | O | N | D
C1. Institutionalization of the Sectoral Action within ANDESCO
A1. Organizational adjustments and funding strategy for the Sectoral Action
|  |  | Capacity building and organisational adjustments plan for the integration of the Sectoral Action within ANDESCO’s core business implemented |  |  | D |  | P |  |  |  |  | E | [7 empty] | …
|  |  | Funding strategy for the Sectoral Action developed and implemented |  |  |  |  | D |  | P |  |  |  |  | E | [5 empty] | …
A2.Capacity building to strengthen the Sectoral Action towards a wider range of corporate development topics
|  |  | Monitoring and evaluation systems for new corporate development topics designed and implemented within the Sectoral Action |  |  |  |  | D |  | P |  |  |  |  | E |  |  |  |  | C
|  |  | Sectoral Action improvement plans related to new strategic corporate development indicators developed | [13 empty] | D | P |  | E | …
A3. Development of public goods and knowledge management
|  |  | Knowledge products developed |  |  | D |  | P |  |  |  |  | E | [7 empty] | …
|  |  | Courses developed and delivered |  |  | D |  | P |  |  |  |  | E | [7 empty] | …
Web module for networking and knowledge exchange developed
A4. Dissemination to stakeholders at the national, regional and international level
|  |  | Dissemination plan of products and knowledge to stakeholders designed and implemented | [8 empty] | D | P |  |  |  | E |  |  |  | …
|  |  | Launching event "Conexión Agua" |  | D |  |  | P | E
|  |  | Andesco Congress | [7 empty] | D |  | P | E
International presentations delivered to position the Sectoral Action
C2. Institutionalization of the WOP-Colombia platform within ACODAL
A1. Organizational adjustments and funding strategy for the WOP platform
|  |  | Capacity building and organizational adjustments plan for the integration of the WOP-Colombia within ACODAL´s core business implemented | [6 empty] | D |  | P |  |  |  | E |  |  |  |  | …
|  |  | Funding strategy for WOP-Colombia designed and implemented | [8 empty] | D | P |  |  |  | E |  |  |  | …
A2.Expanding technical support between utilities based on the partnership model (peer-to-peer).
|  |  | Partnerships between water operators completed |  |  | D |  | P |  |  |  |  | E | [7 empty] | …
A3. Public goods development and knowledge management
|  |  | Business cases documented | [9 empty] | D |  | P |  |  | E |  |  | …
|  |  | Web module for networking and knowledge exchange developed |  |  | D |  | P |  |  |  |  | E | [7 empty] | C
A4. Dissemination to stakeholders at the national, regional and international level
|  |  | Workshops organised to disseminate WOP-Colombia products and knowledge |  |  | D |  | P |  |  |  |  | E | [7 empty] | …
|  |  | Acodal Congress |  |  |  | D |  |  | P |  | E
International presentations delivered to position the achievements of WOP-Colombia
C3. Executing Team
|  |  | Project Planning and Management Specialist | P |  | E
|  |  | Corporate Development Specialist | P |  | E
|  |  | Procurement and Administrative Specialist | P |  | E
|  |  | Sector Specialist | P |  | E

## PEP ESP
CHF |  |  | 1.1
TRM |  |  | 3800
Conexión Agua - Planeación Multianual
| Actividades |  |  | Cantidad | Monto | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
[6 empty] | E | F | M | A | M | J | JL | A | S | O | N | D | E | F | M | A | M | J | JL | A | S | O | N | D | E | F | M | A | M | J | JL | A | S | O | N | D | E | F | M
| Eventos |  |  |  | 1660999.9
Acción Sectorial
Seminario de Acueducto - Barranquilla | bar: 2025 F
Evento de Lanzamiento Conexión Agua (21 marzo) | bar: 2025 M
Congreso ANDESCO Suiza puede ser pais invitado - Cámara de Comercio Colombo-Suiza, AquaData, Asamblea AS | bar: 2025 J
| C1. Institucionalización de la Acción Sectorial |  |  |  | 1660999.9
|  | A1. Ajustes organizacionales de ANDESCO y estrategia de financiación de la Acción Sectorial |  |  | 70000
|  |  | Plan de desarrollo de capacidades y ajustes organizacionales para la integración de la Acción Sectorial dentro de ANDESCO implementado | 1 | 60000 | 2025 F: T; 2025 M: C; 2025 J: E; 2026 E: C
|  |  | Estrategia de financiación para la Acción Sectorial desarrollada e implementada | 1 | 10000 | 2025 M: T; 2025 A: C; 2025 JL: E; 2026 E: C
|  | A2.Desarrollo de capacidades para fortalecer la Acción Sectorial hacia una gama más amplia de temas de desarrollo corporativo |  |  | 601500
|  |  | Sistemas de seguimiento y evaluación de nuevos temas de desarrollo corporativo diseñados e implementados dentro de la Acción Sectorial | 1 | 27000 | 2025 M: T; 2025 A: C; 2025 JL: E; 2025 D: C
|  |  | Planes de mejora de Acción Sectorial relacionados con nuevos indicadores estratégicos de desarrollo corporativo | 3 | 574500 | 2025 S: T; 2025 O: C; 2025 D: E; 2027 N: C
Plan de mejora 1 | bar: 2025 D to 2026 D
Plan de mejora 2 | bar: 2026 M to 2027 J
Plan de mejora 3 | bar: 2026 D to 2027 N
|  | A3. Desarrollo de bienes públicos y gestión del conocimiento |  |  | 817999.9
|  |  | Productos de conocimiento desarrollados | 3 | 459999.9 | 2025 F: T; 2025 M: C; 2025 J: E; 2026 D: C
|  |  | Cursos Técnicos desarrollados y disponibles | 2 | 140000 | 2025 F: T; 2025 M: C; 2025 J: E; 2026 D: C
|  |  | Cursos corporativos desarrollados y disponibles | 2 | 140000 | 2025 F: T; 2025 M: C; 2025 J: E; 2026 D: C
|  |  | Módulo web para networking e intercambio de conocimientos desarrollados | 1 | 78000 | 2026 E: T; 2026 F: C; 2026 M: E; 2026 O: C
|  | A4. Difusión a los grupos de interés a nivel nacional, regional e internacional |  |  | 171500
|  |  | Plan de difusión de productos y conocimientos diseñado e implementado | 1 | 146500 | 2025 M: T; 2025 J: C; 2025 S: E; 2027 A: C
Acción Sectorial | bar: 2025 M to 2027 A
|  |  | Seminario de Acueducto - Barranquilla | 1
|  |  | Evento de Lanzamiento Conexión Agua (21 marzo) | 1
|  |  | Congreso ANDESCO Suiza puede ser pais invitado - Cámara de Comercio Colombo-Suiza, AquaData, Asamblea AS | 1
|  |  | Presentaciones internacionales realizadas para posicionar la Acción Sectorial | 1
|  |  | Evento Gobernanza OCDE - Chile | 1
| C2. Institutionalization of the WOP-Colombia platform within ACODAL |  |  |  | 448000
|  | A1. Organizational adjustments and funding strategy for the WOP platform |  |  | 40000
|  |  | Capacity building and organizational adjustments plan for the integration of the WOP-Colombia within ACODAL´s core business implemented | 1 | 30000 | 2025 A: D; 2025 M: P; 2025 A: E; 2026 M: C
|  |  | Funding strategy for WOP-Colombia designed and implemented | 1 | 10000 | 2025 M: D; 2025 J: P; 2025 S: E; 2026 M: C
|  | A2.Expanding technical support between utilities based on the partnership model (peer-to-peer). |  |  | 285000
|  |  | Partnerships between water operators completed 2025 | 2 | 38000 | 2025 M: P; 2025 J: E; 2025 D: C
|  |  | Partnerships between water operators completed 2026 | 5 | 95000 | 2025 JL: P; 2025 S: E; 2026 D: C
|  |  | Partnerships between water operators completed 2027 | 8 | 152000 | bar: 2026 F to 2027 D
|  | A3. Public goods development and knowledge management |  |  | 53000
|  |  | Business cases documented | 6 | 18000 | 2025 J: D; 2025 JL: P; 2025 O: E; 2027 S: C
|  |  | Web module for networking and knowledge exchange developed | 1 | 35000 | 2025 F: D; 2025 M: P; 2025 J: E; 2025 D: C
|  | A4. Dissemination to stakeholders at the national, regional and international level |  |  | 70000
|  |  | Workshops organised to disseminate WOP-Colombia products and knowledge | 3 | 45000 | bar: 2025 J to 2025 N; 2026 A to 2026 S; 2027 A to 2027 S
|  |  | International presentations delivered to position the achievements of WOP-Colombia | 1 | 25000 | 2026 D: D; 2027 E: P; 2027 M: E; 2027 M: C
| C3. Executing Team |  |  |  | 875000
|  |  | Project Planning and Management Specialist | 1 | 311500 | 2025 E: P; 2025 F: E; 2028 E: C
|  |  | Corporate Development Specialist | 1 | 235500 | 2025 E: P; 2025 F: E; 2028 E: C
|  |  | Procurement and Administrative Specialist | 1 | 179000 | 2025 E: P; 2025 F: E; 2028 E: C
|  |  | Sector Specialist | 0.3 | 145000 | 2025 E: P; 2025 F: E; 2026 A: C
|  |  | Travel expenses (Team Leader) | 1 | 4000
| C4. Audits |  |  |  | 13600
|  |  | ACODAL audit | 1 | 13600 | 2027 A: D; 2027 S: P; 2027 D: E; 2028 F: C
| C5. Contingencies |  |  |  | 110400
|  |  | Contingencies |  | 110400
Cierre Administrativo del Programa | bar: 2028 E to 2028 M
| TOTAL |  |  |  | 3107999.9
Términos de Referencia
Contratación
Ejecución
Cierre